## Assumptions
AI-enabled claims transformation: business case model
Owner: Claims Finance · Version 0.9 (draft) · Synthetic demo data for a fictional insurer
Assumption | Value | Unit | Source / note
Addressable claims cost (motor and home) | 4500 | A$m | FY26 actuals
Current leakage rate | 6% | % | Management estimate; not validated by Internal Audit or Appointed Actuary
Leakage reduction from AI | 30% | % | Industry studies
Realisation factor | 68% | % | Management judgement
Claims handling efficiency at full run rate | 25 | A$m p.a. | Vendor estimate
Discount rate | 9% | % | Group hurdle rate
Net insurance revenue FY26 (for COR impact) | 9260 | A$m | Annual Report 2026, p7
Full run-rate leakage benefit (A$m) | 55.08
Full run-rate total benefit (A$m) | 80.08

## Cash flows
Cash flows (A$m)
Line | FY27 | FY28 | FY29 | FY30 | FY31 | Total
Platform implementation | 18 | 12 | 6 | 0 | 0 | 36
Data migration and integration | 6 | 6.5 | 4 | 0 | 0 | 16.5
Change management and training | 4 | 4 | 3.5 | 0 | 0 | 11.5
Contingency | 2 | 3.5 | 2 | 0 | 0 | 7.5
One-off investment | 30 | 26 | 15.5 | 0 | 0 | 71.5
Run costs: licence and support | 4 | 9 | 12 | 12 | 12 | 49
Benefit ramp (% of full run rate) | 10% | 50% | 90% | 100% | 100%
Benefits | 8.008 | 40.04 | 72.072 | 80.08 | 80.08 | 280.28
Net cash flow | -25.992 | 5.04 | 44.572 | 68.08 | 68.08 | 159.78
Cumulative net cash flow | -25.992 | -20.952 | 23.62 | 91.7 | 159.78
Payback helper (years) | 0 | 0 | 2.4701 | 0 | 0
Payback (years from start of FY27) | 2.4701
Payback (months) | 29.6409
NPV at discount rate, FY27–FY31 (A$m) | 107.2909
Total investment incl. contingency (A$m) | 71.5
COR improvement at full run rate (pts) | 0.73521
Blue = inputs · black = formulas · yellow = key assumptions (Assumptions sheet).